## Sheet1
| 2023-02-01 | [20 empty] | 2023-03-01 | [30 empty] | 2023-04-01 | [29 empty] | 2023-05-01 | [30 empty] | 2023-06-01 | [29 empty] | 2023-07-01 | [30 empty] | 2023-08-01 | [30 empty] | 2023-09-01
| 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat
Simulation study and data analysis
Establish all starting parameters for simulation scenarios, based on data/literature | [54 empty] | continue simulation work throughout April/before fieldwork starts - tasks may need updating
Edit/finish algorithm for burbot population
Model catch rates as function of trapping methods
Create function for tag-recovery process
Summarize data from 2021-2022 burbot tagging for FFSBC
research creel survey data analysis methods - how to estimate total catch, total recovery rates etc
Research costs of different trapping/capture methods | [54 empty] | cost-effectiveness analysis following Braun approach
Creel survey design
Create info sheet/consent form document | [12 empty] | Revise | [6 empty] | Meet with Zoe to discuss/revise
Research and decide on number of sampling days, interview schedule
Book campsite for Carp Lake survey weeks/weekends | [47 empty] | not sure how early campsites can be booked but do this as early as possible, once dates picked out
Fill out risk assessment form (do research on ethics in fisheries)
Create calendar for the summer, coordinate with Zoe (+ others?) on administering surveys
Permits, approvals and reports
Apply REB approval for creel surveys | [33 empty] | Apply to REB this week ~2mo before fieldwork
Apply for new SFCP | [19 empty] | Apply for SFCP early March (2022 report already submitted)
Apply for ACUC renewal | [19 empty] | Apply ACUC renewal
FFSBC progress report due
Field logistics
Book Bert's Cabin for sampling dates |  |  | done - just apply code for RPA fund when reconciling
Inventory Floy tags and order more if needed
Decide whether double-tagging
Generate sets of trapping points, print maps, save gpx files | [82 empty] | Find a time when BC Parks/ministry staff available to pickup/organize traps
Confirm boat crews for 4 weeks | [40 empty] | depends on BC Parks staff, but try to decide/confirm crews in March
Retrieve cod traps, prep buoys/ropes
Prepare tagging kit, assemble all gear
Fieldwork
Carp Lake tagging | [103 empty] | Carp Lake Burbot tagging Wk 1 | [6 empty] | Carp Lake Burbot tagging Wk 2 | [6 empty] | Carp Lake Burbot tagging Wk 3 | [6 empty] | Carp Lake Burbot tagging Wk 4
Carp Lake creel surveys | [131 empty] | Creel Week 1 |  |  |  |  | Wknd 2 | [6 empty] | Wknd 3 |  | Week 3 |  |  |  |  | Wknd 4 | [8 empty] | Week 5 | [18 empty] | Wknd 8 | [6 empty] | Wknd 9 |  | Week 9 | [18 empty] | Wknd 12 |  | Week 12 |  |  |  |  | Wknd 13 |  | Week 13
When done